## Sheet1
| Activity | 2022-01-01 |  |  |  |  | 2022-02-01 |  |  |  | 2022-03-01 |  |  |  | 2022-04-01 |  |  |  | 2022-05-01 |  |  |  |  | 2022-06-01 |  |  |  | 2022-07-01 |  |  |  | 2022-08-01 |  |  |  |  | 2022-09-01 |  |  |  | 2022-10-01 |  |  |  |  | 2022-11-01 |  |  |  | 2022-12-01 |  |  |  | 2023-01-01 |  |  |  |  | 2023-02-01 |  |  |  | 2023-03-01 |  |  |  | 2023-04-01 |  |  |  | 2023-05-01
|  | 3rd | 10th | 17th | 24th | 31st | 7th | 14th | 21st | 28th | 7th | 14th | 21st | 28th | 4th | 11th | 18th | 25th | 2nd | 9th | 16th | 23rd | 30th | 6th | 13th | 20th | 27th | 4th | 11th | 18th | 25th | 1st | 8th | 15th | 22nd | 29th | 5th | 12th | 19th | 26th | 3rd | 10th | 17th | 24th | 31st | 7th | 14th | 21st | 28th | 5th | 12th | 19th | 26th | 2nd | 9th | 16th | 23rd | 30th | 6th | 13th | 20th | 27th | 6th | 13th | 20th | 27th | 3rd | 10th | 17th | 24th | 1st | 8th | 15th | 22nd | 29th
A1 | WBA consultation | bar: 2022-01-01 3rd to 2022-01-01 31st
A2 | Local Scrutiny Panels | bar: 2022-01-01 3rd to 2022-01-01 31st
A3 | Revise WBA | bar: 2022-01-01 3rd to 2022-02-01 28th
A4 | PSB sign off | 2022-03-01 7th: 10
A5 | Translation etc. | bar: 2022-01-01 3rd to 2022-04-01 18th
A6 | Publish Assessment | 2022-05-01 2nd: 5
P1 | Cross reference exsisting objectives (5 WBP) | bar: 2022-01-01 3rd to 2022-01-01 17th
P2 | Delivery of previous priorities | bar: 2022-01-01 3rd to 2022-01-01 17th
P3 | Develop prioritisation methodology | bar: 2022-01-01 3rd to 2022-01-01 31st
P4 | PSB agree endorse methodology | 2022-02-01 14th: 14
P5 | Identify issues for response analysis | bar: 2022-01-01 3rd to 2022-02-01 28th
P6 | PSB agree issues for response | 2022-03-01 7th: 10
P7 | Response analysis | bar: 2022-01-01 3rd to 2022-06-01 13th
P8 | Advice of the FGCO (14 weeks) | bar: 2022-01-01 3rd to 2022-08-01 15th
P9 | PSB agree draft outline objectives | 2022-06-01 27th: 30
P10 | Drafting WBP | bar: 2022-01-01 3rd to 2022-08-01 22nd
P11 | Proof/ translate draft plan | bar: 2022-01-01 3rd to 2022-09-01 26th
P12 | PSB sign off draft | 2022-09-01 26th: 29
P13 | Formal consultation (12 weeks) | bar: 2022-01-01 3rd to 2022-12-01 19th
P14 | Scrutiny | bar: 2022-01-01 3rd to 2022-11-01 28th
P15 | Revision | bar: 2022-01-01 3rd to 2023-01-01 30th
P16 | Sign off by member organisations (and LDGs) | bar: 2022-01-01 3rd to 2023-02-01 13th
P17 | Final sign off by Gwent PSB | 2023-03-01 13th: 16
P18 | Design
P19 | Translation and proofing
P20 | Publish Well-being plan | 2023-05-01 1st: 5
Pre-election period | bar: 2022-03-01 28th to 2022-05-01 2nd
| Gwent PSB meetings | 2022-02-01 14th: 14; 2022-03-01 7th: 10; 2022-06-01 27th: 30; 2022-09-01 26th: 29; 2022-12-01 12th: 15; 2023-03-01 13th: 16
| GSWAG | 2022-01-01 31st: 3; 2022-05-01 23rd: 26; 2022-08-01 29th: 1; 2022-11-01 14th: 17; 2023-02-01 13th: 16; 2023-05-01 22nd: 25 | 24th Aug | 16th Nov
Scrutiny
BG Scrutiny
| Caerphilly Scrutiny | 2022-01-01 24th: 27
Monmouthshire Scrutiny
Newport Scrutiny
| Torfaen Scrutiny | 2022-01-01 31st: 3; 2022-02-01 28th: 2
Local legacy group
| BG Local Delivery Group | 2022-01-01 24th: 25; 2022-03-01 14th: 15; 2022-06-01 6th: 6; 2022-09-01 5th: 5; 2022-11-01 21st: 21; 2023-02-01 20th: 20; 2023-05-01 22nd: 22 | 4th Sept | 20th Nov
| Caerphilly Local Delivery Group | 2022-02-01 14th: 16; 2022-06-01 6th: 8; 2022-09-01 5th: 8; 2022-11-01 21st: 23; 2023-02-01 27th: 28
Monmouthshire Local Delivery Group
Newport Local Delivery Group
| Torfaen Local Delivery Group | 2022-01-01 24th: 24; 2022-04-01 4th: 4; 2022-07-01 25th: 25; 2022-10-01 24th: 24; 2023-01-01 23rd: 23; 2023-04-01 10th: 10 | 17th July | 16th Oct | 22nd Jan
Cabinet
BG Cabinet
Caerphilly Cabinet
Monmouthshire Cabinet
Newport Cabinet
Torfaen Cabinet
Full council
BG Full Council
Caerphilly Full Council
Monmouthshire Full Council
Newport Full Council
| Torfaen Full Council | 2022-01-01 24th: 25; 2022-02-01 28th: 3; 2022-05-01 23rd: 24
ABUHB
NRW
Gwent Police
Gwent PCC
SWFRS
GAVO Management Team
TVA Management Team