## Schedule
'Gwent: Marmot Region' - Programme Timeline
v0.10
ABGPHT: Lead: Stuart Bourne CPH; Interim Programme Manager: Richard Lewis PPHP
| Week commencing (2022) | [41 empty] | 2023
ACTIVITY - ABGPHT PROGRAMME LEAD & PROGRAMME SUPPORT | time axis 2022-03-14 to 2023-06-26
Programe Team Annual Leave | 2022-04-11: RL; 2022-05-16: SB; 2022-05-30: RL 31+1; 2022-06-20: SB; 2022-07-18: RL 0.5 DAY - 22; 2022-08-01: RL 2-4; 2022-08-08: RL; 2022-08-15: RL; 2022-09-26: RL 0.5 DAY - 30
Meeting with (Caerphilly CBC) Gwent PSB Secretariat (PC/HD) | 2022-03-14: 17; 2022-03-21: 24; 2022-04-11: TBC
Meeting with Institute of Health Equity (TB) | 2022-03-21: 23; 2022-04-25: 28; 2022-05-16: 17; 2022-06-06: TBA
Draft JD/PS job roles in ABGPHT - Bands 8a, 7, 6 (RL with SC) | bar: 2022-03-21 to 2022-04-04
Job roles matched & approved for recruitment (SC) | bar: 2022-04-11 to 2022-05-16
Job roles advertised (SC) | bar: 2022-05-23 to 2022-06-13
Shortlisting (SB & RL) | bar: 2022-06-27
Interviews & offers (SB) | bar: 2022-07-11
Meeting with ABUHB Strategic Communcations Lead, Population Health (SW-E) | 2022-03-28: 31
Meeting with ABUHB Deputy Director of Planning on IMTP | 2022-04-04: 7; 2022-06-06: TBA
Meeting with Service Manager, Gwent Regional Partnership Board (PD) | 2022-04-25: 28
Meeting with WHESRi Team in WHOCC, PHW (RH, LC) | 2022-04-25: 27
Reading for 'Response Analysis' (WG and OFGC guidance, WBA, PNA) | bar: 2022-03-14 to 2022-04-25
IHE contract signed & payment made | bar: 2022-03-14 to 2022-04-04
SLA drafted and agreed with IHE | bar: 2022-03-28 to 2022-05-09
IHE start | bar: 2022-06-06
Planning and preparation for IHE workshops | bar: 2022-06-13 to 2022-07-25
Evaluation framework developed | bar: 2022-07-04 to 2022-07-25
Launch event invitations | bar: 2022-08-01 to 2022-08-08
LA workshop invitations | bar: 2022-08-15 to 2022-08-29
Launch event | bar: 2022-09-12 to 2022-09-19
Delivery of workshops | bar: 2022-10-03 to 2022-11-28
Report: analysis of health inequalities in Gwent | bar: 2022-07-04 to 2022-10-31
In conversation' with Professor Marmot and Dr Aitken | bar: 2022-09-12 to 2022-09-19
Delivery of narrative for public involvement/conversation on health inequalities | bar: 2022-11-07 to 2022-12-26
Final report inc recommendations and case studies | bar: 2022-12-05 to 2023-05-22
Launch event for final report | bar: 2023-05-29 to 2023-06-05
Facilitating IHE attendance at Gwent PSB to discuss published Well-being Plan / deliver CPD | 2023-06-19: 22
Marmot Region update paper: draft to SA (RL/SB) | 2022-05-23: 23
Marmot Region update paper: draft to GSWAG (RL/SB) | 2022-05-16: 19
Marmot Region update paper: draft to CEOs (RL/SB) | 2022-05-30: 30
Marmot Region update paper: submit to PSB (RL/SB) | 2022-06-13: 16
Marmot Region update paper: submit to ABUHB PPPH Committee (RL/SB) | 2022-06-20: Tbc
Marmot Region Leadership Programme Group est | bar: 2022-07-04
Meeting with Gwent PSB Engagement Group - RL, SW-E | 2022-04-18: 22
Develop draft Communications and Engagement Plan - SW-E | bar: 2022-04-04 to 2022-04-25
| Week commencing (2022) | [41 empty] | 2023
GWENT PSB HEADLINE TIMETABLE - RESPONSE ANALYSIS & WELL-BEING PLAN 2023-2028 | time axis 2022-03-14 to 2023-06-26
GSWAG meeting | 2022-03-28: 29; 2022-04-18: 21; 2022-05-23: 26; 2022-08-29: 1; 2022-11-14: 17
PSB meeting | 2022-06-27: 30; 2022-09-26: 29
Publish Gwent Well-being Assessment | 2022-05-02: 5
Develop Response Analysis | bar: 2022-03-14 to 2022-06-13
Advice of the Office of Future Generations Commissioner (14 weeks) | bar: 2022-05-02 to 2022-08-01
Draft Gwent Well-Being Plan | bar: 2022-07-04 to 2022-08-22
PSB meeting - sign-off draft Gwent Well-being Plan | 2022-09-26: 29
Formal consultation (12 weeks) | bar: 2022-10-03 to 2022-12-19
Sign-off Gwent Well-being Plan (PSB organisations and Local Delivery Groups) | bar: 2023-01-02 to 2023-02-13
Final sign-off Gwent Well-being Plan (Gwent PSB) | 2023-03-13: 16
Publish Gwent Well-being Plan | 2023-05-01: 5