## Sheet1
| Activity | 2022-06-01 |  |  |  | 2022-07-01 |  |  |  | 2022-08-01 |  |  |  |  | 2022-09-01 |  |  |  | 2022-10-01 |  |  |  |  | 2022-11-01 |  |  |  | 2022-12-01 |  |  |  | 2023-01-01 |  |  |  |  | 2023-02-01 |  |  |  | 2023-03-01 |  |  |  | 2023-04-01 |  |  |  | 2023-05-01
|  | 6th | 13th | 20th | 27th | 4th | 11th | 18th | 25th | 1st | 8th | 15th | 22nd | 29th | 5th | 12th | 19th | 26th | 3rd | 10th | 17th | 24th | 31st | 7th | 14th | 21st | 28th | 5th | 12th | 19th | 26th | 2nd | 9th | 16th | 23rd | 30th | 6th | 13th | 20th | 27th | 6th | 13th | 20th | 27th | 3rd | 10th | 17th | 24th | 1st | 8th | 15th | 22nd | 29th
P1 | Cross reference exsisting objectives (5 WBP)
P2 | Delivery of previous priorities
P3 | Develop prioritisation methodology
P4 | PSB agree endorse methodology
P5 | Identify issues for response analysis
P6 | PSB agree issues for response
P7 | Response analysis | bar: 2022-06-01 6th to 2022-06-01 13th
P8 | Advice of the FGCO (14 weeks) | bar: 2022-06-01 6th to 2022-09-01 12th
P9 | PSB agree draft outline objectives | 2022-06-01 27th: 30
P10 | Drafting WBP | bar: 2022-06-01 6th to 2022-08-01 22nd
P11 | Proof/ translate draft plan | bar: 2022-06-01 6th to 2022-09-01 26th
P12 | PSB sign off draft | 2022-09-01 26th: 29
P13 | Formal consultation (12 weeks) | bar: 2022-06-01 6th to 2022-12-01 19th
P14 | Scrutiny | bar: 2022-06-01 6th to 2022-11-01 28th
P15 | Revision | bar: 2022-06-01 6th to 2023-01-01 30th
P16 | Sign off by member organisations (and LDGs) | bar: 2022-06-01 6th to 2023-02-01 13th
P17 | Final sign off by Gwent PSB | 2023-03-01 13th: 16
P18 | Design | bar: 2022-06-01 6th to 2023-04-01 17th
P19 | Translation and proofing | bar: 2022-06-01 6th to 2023-04-01 17th
P20 | Publish Well-being plan | 2023-05-01 1st: 5
| Gwent PSB meetings | 2022-06-01 27th: 30; 2022-09-01 26th: 29; 2022-12-01 12th: 15; 2023-03-01 13th: 16
| GSWAG | 2022-08-01 29th: 1; 2022-10-01 10th: 13; 2022-11-01 14th: 17; 2023-02-01 13th: 16; 2023-05-01 22nd: 25 | 24th Aug | 16th Nov
Scrutiny
BG Scrutiny
Caerphilly Scrutiny | bar: 2022-10-01 31st
Monmouthshire Scrutiny
Newport Scrutiny
Torfaen Scrutiny
Local legacy group
| BG Local Delivery Group | 2022-06-01 6th: 6; 2022-09-01 5th: 5; 2022-11-01 21st: 21; 2023-02-01 20th: 20; 2023-05-01 22nd: 22 | 4th Sept | 20th Nov
| Caerphilly Local Delivery Group | 2022-06-01 6th: 8; 2022-09-01 5th: 8; 2022-11-01 21st: 22; 2023-02-01 27th: 28
Monmouthshire Local Delivery Group
Newport Local Delivery Group
| Torfaen Local Delivery Group | 2022-07-01 25th: 25; 2022-10-01 24th: 24; 2023-01-01 23rd: 23; 2023-04-01 10th: 10 | 17th July | 16th Oct | 22nd Jan
Full council
BG Full Council
Caerphilly Full Council
Monmouthshire Full Council
Newport Full Council
Torfaen Full Council
ABUHB
NRW
Gwent Police
Gwent PCC
SWFRS
GAVO Management Team
TVA Management Team