****

**Delivery Plan 2024+**

**Priority Area: TOWN CENTRES**

|  |  |
| --- | --- |
| **INPUTS: Potential ‘resources’ that you’re aware of that could help achieve the outcomes** | |
| **Outcome** What are we trying to do and why? | Improve attractiveness, increase footfall, aid vibrancy and sustainability. |
| **Lead officer** | Allan Dallimore |
| **Policy Support Officer** | Paul Hudson |
| **What do we have:** For example, skills, knowledge, experience of teams, officers; budget; assets (land, built assets, equipment, vehicles, etc); policies, strategies, programmes, plans; current/planned initiatives; anything else?  Experienced, knowledgeable staff within the Business and Enterprise Renewal Team and wider experience officers within other LA departments. Good working relationships with businesses, town councils and other organisations to aid outcomes. Existing land, and property assets including equipment. Existing delivery partners, existing budgets, strategies and programmes.  We have grants programmes aimed at bringing properties back into beneficial use.  SPF investment plan currently being delivered together with transforming towns programme. There is an overarching Economic Regeneration Strategy being developed with an emphasis on town centre regeneration and there are a number of Placemaking plans being developed for our town centres.  In addition to this we have an SPF intervention aimed at delivering a Meanwhile Space program for the benefit of businesses and voluntary organisations and other partners. | |
| **Delivery partners:** Name, organisation and contact details  Local businesses, landowners, housing associations, private sector landlords, adjacent local authorities, Welsh Government Regeneration Department, transport operators, Caerphilly Business Club and their partners, Urban Foundry and Pop Up Wales  Partnership working with Coleg Y Cymoedd to share resources | |
| **Collaborations:** For example, groups, networks, forums, partnerships  Caerphilly County Borough Council - the development of the Masterplan has drawn upon the expertise from key representatives from across local authority departments, including Planning, Regeneration, Housing.  Placemaking Plans in collaboration with the Design Commission for Wales and developed in line with the Wales Placemaking Charter.  Caerphilly Business Club  PSB  Caerphilly 2035 Programme Board  Caerphilly 2035 Executive Group  WG Regeneration Officer network  WLGA Regeneration Forum  Association of Town Centre Managers  Coleg y Cymoedd  Town Square  Educate  JCP Solicitors  Einfinity  Construction Hub  Welsh Ice  Alliance Wales and West  Visit Caerphilly  Venture Graduates | |
| **Stakeholders:** For example, communities, landowners, businesses etc.  Businesses, landowners, housing associations, private sector landlords, adjacent local authorities, government organisations, transport operators, education providers, town councils, elected members, Caerphilly Business Club, local community groups and other partner organisations/stakeholders. | |
| **Funding streams:**  UK and Welsh government funding streams e.g. SPF, Levelling Up, Transforming Towns, Town Council and community funds, LA budgets, private investment, LA borrowing. | |
| **Good practice resources:** For example, case studies, examples of good practice initiatives; guidance, toolkits; training, learning, development opportunities  Existing Regeneration Strategy which defines the benefits of town centres and the role they play in regenerative activity,  LDP Masterplans outline strategic goals of town centres as centres of activity whilst the Placemaking Plans go into greater granular detail, Place shaping Plan, Caerphilly 2035 (Ffos Caerffili), Town Centre Audits. | |

**Activities** add more lines if needed.

|  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| **Ref** | **Key Tasks** | **Lead** | **Partners** | **By when** | **BRAG** |
|  | Community Cohesion – utilise SPF funding to undertake town centre public realm improvement projects in our main town centres | Business Enterprise and Renewal Team | Community groups, town council, businesses, community groups |  |  |
|  | Meanwhile Spaces – provide Start Up opportunities | Urban Foundry/Pop Up Wales/Town Centres |  | March 25 |  |
|  | Town Centre Improvements – using the Town Centre Audits as the main driver to improve visitor perception, attract more businesses and encourage greater footfall. | Business Enterprise and Renewal Team | Other LA departments, other organisations/businesses | March 25 |  |
|  | Completion of Regeneration Strategy and Placemaking Plans. | Business Enterprise and Renewal Team | Other LA departments, other organisations/businesses  Private Investors | End Summer 24 |  |
|  | Identify and secure funding for key projects within Placemaking Plans. | Business Enterprise and Renewal Team | Other LA departments, other organisations/businesses  Private Investors |  |  |

**Critical links with other Priority Areas** (grey out this Priority Area)

|  |  |
| --- | --- |
| Housing | Working on ensuring sustainable housing in town centres and tackling vacancy rates |
| Town Centres/Community Hubs | Identifying opportunities for greater community activity in our town centres |
| Employability | Developing more diverse work opportunities in our town centres including new Meanwhile Spaces |
| Decarbonisation | Using the tools available to us to ensure our town centres reduce their carbon footprint |

**Who else needs to be involved** are there people/groups/organisations that can help to deliver the priority

|  |  |  |
| --- | --- | --- |
| Who | What can they bring/why should they be involved | How will you include them |
| Businesses | Feedback and knowledge | Consultation, questionnaires, town centre stakeholder meetings |
| Town Councils | Funding and knowledge | Consultation, questionnaires, town centre stakeholder meetings |
| Community Groups | Feedback and knowledge | Consultation, questionnaires, town centre stakeholder meetings |
| Elected Members | Support, feedback | Consultation, questionnaires, town centre stakeholder meetings |
| Government Organisations | Funding and guidance | Communication channels |

**Risks** are there any risks you have identified.

|  |  |  |  |
| --- | --- | --- | --- |
| **Actual risks** | **Risk rating** (low/medium/high) | **How will you manage/mitigate this risk** – what are you doing to reduce the risk | **Risk owner** |
| Funding - Funding streams are drying up | High | Awareness of all funding opportunities and private investment available. | Lead Organisation |
| Internal Resources - not having enough human resource to drive activity forward | High | Look to build posts into bids that are submitted for external funding | Business Enterprise and Renewal Team |
| Politics | High | Take all options into consideration | Lead Organisation |
| Change of Policies | High | Be mindful of change, consider contingency plans | Lead Organisation |

**Well-being of Future Generations Act – 5 Ways of Working**

Have you considered the Ways of Working in the development of your actions? (tick where appropriate)

|  |  |  |  |  |
| --- | --- | --- | --- | --- |
| Long term | Prevention | Integration | Collaboration | Involvement |
| ✓ | ✓ | ✓ | ✓ | ✓ |

More information is available here: <https://www.futuregenerations.wales/about-us/future-generations-act/>

**Measures of success** how will you know if you’re making a difference

|  |
| --- |
| Triennual town centre surveys  Feedback from business community at business events held in town centres e.g. Stakeholder Meetings, Caerphilly Business Club Meetings  The number of projects delivered/completed, evaluation of completed projects  Case Studies  The amount of inward investment attracted  Reduction in vacancy rates  Increase in footfall  Increase in number of businesses operating out of town centres  Increase in dwellings in town centre locations  Number of community orientated facilities in town centres  . |