SUBJECT:	Safer Places priority update

MEETING:	Gwent Public Services Board

DATE: 11/12/25

Report written and submitted by: Sam Slater, Head of Strategy, Gwent OPCC

| 1 | Areas Affected |
| --- | --- |
| 1.1 1.2 | Geographically, this affects the whole of Gwent and all PSB member organisations. Thematically, this addresses the Gwent Wellbeing Plan priority ‘everyone lives in a place they feel safe’ and the Gwent Community Safety Review, commissioned by the PSB. |
| 2 | Purpose of Report |
| 2.1 | This report provides an update on progress against the above PSB priority (hereafter called the ‘safer places’ priority), following the introduction of the new Gwent Strategic Safer Communities Board (GSSCB) in July 2025. The GSSCB was introduced as a result of the PSB commissioned Community Safety Review and to provide governance for the safer places priority. |
| 3 | Background |
| 3.1 3.2 3.3 3.4 3.5 3.6 3.7 3.8 3.9 | As members will be aware, the PSB agreed to the new terms of reference for the GSSCB in March 2025, the first meeting of the GSSCB was held in July 2025, chaired by the Police and Crime Commissioner. The first meeting was well attended by senior strategic leads from PSB partner agencies and chairs of the relevant safer places partnerships that feed into the GSSCB. At the meeting, the board agreed some final adjustments to the terms of reference to account for the legal oversight requirements of some of the partnerships, and also added some additional members. The final agreed terms of reference are included at Appendix A. The board also agreed to carry out a short review/survey of the various ‘safer places partnerships’ that feed into it. The survey was to focus on improving the collective understanding of their governance arrangements, plans/priorities and current issues the partnerships face, to be carried out during the summer. This work was undertaken and reported back to the GSSCB at the second meeting in September 2025 and used to inform a discussion on priorities. The results of this survey are included at Appendix B. Alongside this work, in late spring the Home Office announced the introduction of the ‘Safer Streets Summer Initiative’ (SSSI). This encouraged PCCs to lead planning for a surge campaign by police and community safety partners in town centres during the summer, focusing on street crime, retail crime and antisocial behaviour. In support of the safer places priority and GSSCB the Commissioner provided £50k to community safety partners to boost the initiative and relevant partners were convened to develop a joint plan across Gwent. SSSI was successfully carried out from July to September and focused on additional police and partnership patrols and enforcement in town centres, alongside engagement with communities and businesses. The overall results of SSSI in Gwent are at Appendix C. The engagement activity with local businesses in Monmouthshire, funded by the PCC, was identified by the Home Office as one of their national highlights of the scheme. The output and learning from SSSI was also included in the planning discussions by the GSSCB when they met again in September. With all of the above activity undertaken, and after a briefing provided by the Head of the Wales Safer Communities Network on upcoming legislative changes, at the September meeting the GSSCB agreed a number of priorities to take forward. The priorities seek to impact on both improving the governance and support to relevant safer places partnerships across Gwent, but also some bespoke practical activity requested to be undertaken by partnerships. The priorities are: - To further survey and map the entirety of the safer places partnerships across Gwent, building on the short survey in the summer and work undertaken in the earlier community safety review. This will enable board members to identify other areas to focus on improving. - To review arrangements for partner agency chairing and attendance at the safer places partnerships and make recommendations to improve their stability and sustainability. - To review the totality of data and analysis requirements from each of the partnerships, and make recommendations to reduce duplication, improve access to information, reduce competition for resources, and link more closely to the Joint Strategic Assessment platform. - To plan for a Winter of Action, similar to SSSI, during the Christmas and winter period, with an enhanced focus on safety in the evening and nighttime economy and violence against women and girls. - To support Gwent Police’s requirement to develop a long-term antisocial behaviour action plan, which is a requirement of the UK Government’s Safer Streets priority – due to be submitted in April 2026. Since the meeting, the September PSB also requested that the GSSCB provide oversight to activity and plans to counter the community cohesion and tension issues experienced over successive summers. This is now an added priority in the work programme. Although it has been a short time since the priorities were agreed in September, some progress has been made against each of the priorities. This has been coordinated through a subgroup that has been formed including the business managers or coordinators of the various safer places partnerships. Collectively, they have agreed to and are supporting the following activities: - A follow-up detailed survey will be sent shortly from the Commissioner’s office to subgroup members to complete relevant mapping. - Separate task and finish groups have been formed, represented by different partnerships, to undertake the reviews into chairing/attendance arrangements and data/analysis planning. The first of the meetings of both groups is planned for late November. - The Commissioner has provided an additional £50k fund from her community safety funding to support the Winter of Action campaign, which community safety partnerships are currently preparing to bid into alongside wider planning. This will be topped up with some PSB funding for engagement activity, whilst Gwent Police are leading on operational planning with partners. The overall plan for Gwent will be coordinated by the Commissioner’s office and submitted to the GSSCB and Home Office at the end of November. - Gwent Police have just initiated planning for the ASB action plan and will engage with partners at the appropriate point. - Conversations have taken place with the police and local authority leads in relation to community cohesion/tensions. They are seeking support to introduce a new structure across Gwent to plan for and respond to issues when they arise. An outline presentation is being prepared for the next GSSCB in early December to agree next steps. Overall, there has been good engagement from partners for the GSSCB and it’s subgroup, and things are now starting to move forward positively. There are some practical steps that should impact positively on the communities of Gwent, alongside some longer term strategic objectives. The next GSSCB meeting will be in early 2026 after the December meeting had to be cancelled. The next meeting will review progress and help steer, shape and agree next steps for the safer places priority. |
| 4 | Funding |
| 4.1 | Resourcing this work is being provided by members of the relevant safer places partnerships, coordinated by the Police and Crime Commissioner’s office. In total this year the PCC has provided an additional £100k to community safety partnerships to support the summer and winter campaigns. The winter campaign is being topped up by an additional £7-8k (exact TBC) from PSB funding for community engagement in support of the objectives, as agreed through the Gwent Strategic Wellbeing Action Group (GSWAG). This welcome funding highlights the ongoing strength of partnership working across Gwent. |
| 5 | Recommendations |
| 5.1 | There are no recommendations for the PSB other than to note the contents of the report. |

Background Documents

Appendix A

Appendix B

Appendix C